## On Going
Module Name | Feature/Requirement | Current Status
Branch Analytics | A centralized analytics module designed to provide branch-wise operational insights across all Narayana branches nationwide. | On Going
Retention Calling | Enable school leadership (VP, Principal) to proactively reach out to students identified as high dropout risk through AI Call Quality Analysis. When Adoption Calling calls are analyzed by NScribe, students flagged with dropout indicators need follow-up intervention to understand and address their concerns. | On Going
Learning & Development | UI and BE revamp & Migration | On Going
Bus Tracking | Fleet Management (Revamp):- 1.UI and backend development mostly completed, including partial permission handling. 2.Initial testing for read-only permissions and related error handling has been completed. 3.Frontend feature visibility is currently dependent on backend permission responses. 4.Backend implementation by @Suresh Gundupalli is completed and under review. 5.Final frontend integration for permission-based access will resume after backend review. Student Mapping (Revamp):- 1.Planning phase is largely complete; moving into technical implementation. 2.Previous attempt for stop detection lacked accuracy. 3.Currently reworking the approach using an improved algorithm. 4.Plan is to conducted on a smaller set of vehicles, with validation against real-world data to ensure accuracy. | On Going
Opinion Poll (Revamp) | Revamp and Migration | On Going
Events & gallery (Revamp) | Module migration and Revamp | On Going
CCTV (Revamp) | Revamp and Migration | On Going
Content Management (Revamp) | Migration | On Going
Meeting's Module(Revamp) | Migration | On Going
User Management (Revamp) | Migrationa and Revamp | On Going
Bun Migration(Performance Improvement Task) | Admin new is pending. | On Going
User Management | enhancements for updating the secondary number in User Management (requirement shared by Tulasi ma’am). | On Going
Announcement Acheivements Module | Announcemnet modules split to send the acheivements seperately fro academic announcements | On Going
Ntrack report | Implementing Distance report and Daily report | On Going
Nscribe | Enhancements | On Going
AI Counsellor | The AI Counsellor is an RAG-based chatbot developed for Narayana Group’s Schools, Junior Colleges, and Coaching Centers to replace existing flow-based bots, aiming to enhance interactive user engagement, reduce costs, customize services, and boost lead conversion rates; its POC, evaluations, and development have been completed, and it is now awaiting for the DM Team’s testing | On Going
Disha Call Analysis | Analyzes all calls by categorizing them based on predefined call types and patterns. This helps in identifying trends, improving response handling, and generating actionable insights from call data. | On Going
Parent Concerns | Tags and Filter Issues | On Going
Wellness Clickhouse integration | Migrated the wellness analytics database from PostgreSQL to ClickHouse to improve performance, | On Going
Events & Gallery Clickhouse integration | Migrated the Event& Gallery database from PostgreSQL to ClickHouse to improve performance, | On Going
Opinionpoll Clickhouse integration | Migrated the Opinion poll database from PostgreSQL to ClickHouse to improve performance, | On Going
Enh: Digital library Mis Report Filter Addition | Added advanced filters to the Digital Library MIS reports to enable easier data segregation, refined analysis, and quicker report generation. | On Going
Parent Concerns | Concern grace period flow along auto closed concern | On Going
Bus Tracking | API Integration GPS devices - Mahindra Student monitoring (live tracking) within our nConnect parent application. | On Going

## Recently Deployed
Module Name | Feature/Requirement | Current Status
Parent Check - in Module(Phase 2) | 1.Add feedback form visibility for completed calls in the Staff App so users can refer to previous feedback before making a new call. 2.Give module access permissions to additional designations such as RI, DGM, CO, RD, and AD. 3.In Analytics view (Admin Panel), add graphical insights for feedback form questions so stakeholders can easily identify gaps and trends. | Recently Deployed
Announcement Creation | Staff can create announcements from staff App as well. | Recently Deployed
Events & gallery (Language addition) | user should be able to post as per student first language | Recently Deployed
nScribe enhancements phase2 | Non-Complaint Calls data is missing, Work Teacher Conversation Score Evals, rubrics Single Month Selection Removal of Raw Report Overtime Graph Fixes | Recently Deployed
House Keeping & Security(Flutter) | Branch & Building Selection in Feedback Form Access Control Before Branch Selection Auto-Select Branch for Single Branch Users Building Dropdown Structure Display Building Details in Preview Update Feedback Form Questions to Past Tense Rename “Overdue” Status to “Submission Missed” in Feedback Forms Add Submission Deadline Subheading Under Daily Tab Feedback Form – Default Option Removal Feedback Form – Submit Button Validation | Recently Deployed
House Keeping & Security(BackEnd) | Replace Designation-Based Access with Permission-Based Access Update Daily Form Availability Window | Recently Deployed
House Keeping & Security(Admin&Web App) | Branch Auth Tab in Admin Panel Branch Auth ID Management Screen Remove Columns from Manpower Distribution Add New Columns "Add Team Leader, AGM, Branch Status" Across All Staff Attendance Tables Add Filters for New Fields Validation for Inactive Branch Upload Display Role-wise Quota & Capture Percentages on Dashboard Add Percentage Column in Export Report Improve Face Capture Guidance in Web App Add “Edit Manpower Distribution” Button Add Row-Level Edit Option in Manpower Distribution Enable Edit in Day-wise Quota Detail Screen Branch Auth ID – Bulk Upload Validations Showcasing a "Enable Location" video guide Admin Panel – Dashboard Report Download Enhancement | Recently Deployed
Fee Payment | Enhanced security on the Legacy Status Check | Recently Deployed
Enable Nscribe AI for college | Enhancement | Recently Deployed
NscribeAI Preset filter | Enhancement | Recently Deployed
Academic year migration | Migrated Partially | Recently Deployed
Program: Prodgy hide the given modules | This is the requirement frowarded through email from JK Fee Payment Opinion Poll Bus Tracking Gate Pass Wellness Removing these module access for the prodigy program | Recently Deployed
Parent Check - in Module | The Parent Check-In Module is designed to enable structured, consistent, and trackable parent feedback collection across all programs in zones under Sharani ma’am using predefined questions via phone calls made through the nConnect Staff App. The system ensures that each parent is contacted once within a monthly cycle and that the feedback collected is standardized, measurable, and actionable for leadership. | Recently Deployed
Hostel Managemnet | Full Module Development | Recently Deployed
MicroSchedule Submission Percentage | To show the submission percentage | Receltly Deployed
Feedback Module(Revamp) | Migration | Recently Deployed
TPT | Currently, VP (Vice Principal) training audits are managed through manual Google Forms and Excel spreadsheets, creating operational inefficiencies, inconsistent evaluation processes, and limited analytics capabilities across our 800+ school network. | Recently Deployed
GPS Dashboard | GPS Device Management Route Management | Recently Deployed
Anouncements Comments Feature | Enable two-way communication on Announcements by allowing parents to add private, 1:1 comment threads that staff/principal can respond to from the admin panel, while keeping the comment space controlled, time-bound, and safe. | Recently Deployed
Gate pass (Revamp) | Module Revamp and Migration | Recently Deployed
SMS(Revamp) | Module Revamp and Migration | Recently Deployed
Financial Dashboard | The Financial Performance module enables real-time tracking and accountability of financial and operational commitments made by AGMs. It provides a dashboard for AGMs and management to compare projected vs. actual performance across key metrics. | Recently Deployed
Wellness(Revamp) | Module Revamp and Migration | Recently Deployed
OBD Protocol Server Implementation | Implemented a dedicated OBD protocol server to enable seamless communication, data processing, and real-time diagnostics between vehicle systems and backend services. | Recently Deployed
Parent Concerns(Revamp) | Module Revamp and Migration | Recently Deployed
Staff Attendance(Revamp) | Module Revamp and Migration | Recently Deployed
Activity Dasboard(Revamp) | Module Revamp and Migration | Recently Deployed
HKS | - Added Building Name and Building SFT columns in Dashboard, Manpower Distribution, and Attendance Record screens. - Added Building filter in Dashboard, Attendance Record, and Manpower Distribution screens. - Split Mess column into Mess Shift 1 and Mess Shift 2 in Branch Summary table. - Added support for consecutive Mess shifts (Shift 1: 6 AM–2 PM, Shift 2: 2 PM–9 PM). - Added Branch Auth ID column in Manpower Distribution download template. - Increased branch radius to 30 km when coordinates are available.A36 | Recently Deployed
Push Notifications | Revamp | Recently Deployed
Admin Panel | Logout feature for staff through Admin panel, To log out all the active sessions from multiple devices | Recently Deployed
GPS Device Management - nTransport | Manages the master list of GPS tracking devices that get installed in school buses and commercial vehicles. | Recently Deployed
Route Management - nTransport | Manages school transport routes, the stops along each route, and which students board at which stop. | Recently Deployed

## Up Coming
Module Name | Change / Enhancement / New Requirement | Current Status
HR Operations | Provide the HR Operations team a single workspace to plan, announce, execute, and report on staff-facing events, with sophisticated audience targeting, automated stakeholder notifications, reach/engagement tracking, and structured records that feed leadership MIS. | UP Coming
Module wise Analytics | Provides branch-wise insights across the nConnect ecosystem by tracking module usage, user engagement, and activity trends for each Narayana branch. This helps identify high-performing branches, underutilized modules, and data-driven improvement opportunities. | Up Coming
Adoption Calling (Revamp) | Full Module migration and Revamp | Up Coming
Adoption Calling | Secondary Mobile Management & Change Logs Problem: Admins need a safer, auditable way to update students'/employees' secondary mobile numbers, prevent misuse (frequent changes, number sharing), and handle emergency cases when the registered parent has lost access. | Up Coming
nScribe Phase 3 | Hierarchical heatmap/OLAP-style explorer An interactive view of Adoption Calling parent conversations, scored Month-Wise - click any state to drill into its branches, segments, and classes, with monthly movement colour-coded for instant scan. Isue Condensation Teacher Score | UP Coming